School Improvement Action Plan School Year:; 2022-2023. School Name:; Campbell Middle School. Principal Name:; Dr. Camille Havis. Date Submitted:; June 10, 2022. Revision Dates:; 6/13/22, 8/19/22, 8/24/22.

| District Name |  | Cobb County School District |
| --- | --- | --- |
| School Name |  | Campbell Middle School |
| Team Lead |  | Camille Havis |
| Position |  | Principal |
| Email |  | Camille.Havis@cobbk12.org |
| Phone |  | 678-842-6873 |
| Federal Funding Options to Be Employed (SWP Schools) in This Plan (Select all that apply) |  |  |
| X | Traditional funding (all Federal funds budgeted separately) |  |
|  | Consolidated funds (state/local and federal funds consolidated) - Pilot systems ONLY |  |
|  | “Fund 400” - Consolidation of Federal funds only |  |
| Factor(s) Used by District to Identify Students in Poverty (Select all that apply) |  |  |
|  | Free/Reduced meal applications |  |
|  | Community Eligibility Program (CEP) - Direct Certification ONLY |  |
| X | Other (if selected, please describe below) |  |
| Direct Certification |  |  |

In developing this plan, briefly describe how the school sought and included advice from individuals (teachers, staff, other school leaders, paraprofessionals, specialized instructional support personnel, parents, community partners, and other stakeholders). References: Schoolwide Checklist 3.b.[Sec. 2103(b)(2)]

School Response: Meetings were held with the Principal’s Advisory Committee in January, February, March, and April. The committee includes teachers, Title 1 staff, PTSA, and local business representatives.

IDENTIFICATION of STAKEHOLDERS

Stakeholders are those individuals with valuable experiences and perspective who will provide the team with important input, feedback, and guidance. Stakeholders must be engaged in the process to meet requirements of participating federal programs. Documentation of stakeholder involvement must be maintained by the school.

| Position/Role | Name |
| --- | --- |
| Title I Supervisor | Lou Ferretti |
| Academic Coach (District) |  |
| Academic Coach (Local School) | Tanika Parrish |
| Parent (Non CCSD Employee) | Latoya Palmer-Addy and Irene Wong |
| Business Partner | Tim Gould and Kim Aaron |
| Counselor | Alex Gorrell |
| Parent Facilitator | Dalia Saldierna |
| Health Care Providers |  |
| Social Workers |  |
| Faith-based Community Leaders |  |
| Technology Experts (TIS) |  |
| Media Specialists/Librarians |  |
| Police/Public or School Safety Officers |  |
| Universities or Institutes of Higher Education |  |

COMMITTEE MEMBERS SIGNATURE PAGE

The comprehensive needs assessment (CNA) and school improvement team (SIP) team consist of people who are responsible for working collaboratively throughout the needs assessment and plan development process. Ideal team members possess knowledge of programs, the capacity to plan and implement the needs assessment, and the ability to ensure stakeholder involvement. Documentation of team member involvement must be maintained by the school.

| Meeting Date(s): | January 24, 2022 / February 15, 2022 / March 14, 2022 / April 25, 2022 |
| --- | --- |

| Position/Role | Printed Name | Signature |
| --- | --- | --- |
| Principal | Dr. Camille Havis |  |
| Academic Coach | Tanika Parrish |  |
| Science Department Lead | Candace Ellis |  |
| PTSA President | Latoya Palmer-Addy |  |
| 8th Grade Parent | Irene Wong |  |
| Business – Smyrna City Council | Tim Gould |  |
| Business – American First Title | Kim Aaron |  |
| Counselor | Alex Gorrell |  |
| Parent Facilitator | Dalia Saldierna |  |

9

Comprehensive Needs Assessment Evaluation of Goal(s)

(References: Schoolwide Checklist 1.a.)

Collaborate with your team to complete the questions below regarding the progress the school has made toward each goal in the FY21 School Improvement Plan (SIP).

| Previous Year’s Goal #1 | Decrease the percentage of students scoring below proficiency by 10% on the Reading Inventory for grades 6-8. |
| --- | --- |
| Was the goal met? ☒ YES ☐ NO |  |
| What data supports the outcome of the goal? | In August of 2021 we had 242 students scoring below proficiency on the Reading Inventory for grade 6-8. In April of 2022 we had 182 students scoring below proficiency on the Reading Inventory for grade 6-8. That is a 24.7% decrease! |
| Reflecting on Outcomes |  |
| If the goal was not met, what actionable strategies could be implemented to address the area of need? |  |
| If the goal was met or exceeded, what processes, action steps, or interventions contributed to the success of the goal and continue to be implemented to sustain progress? | We had targeted reading support classes for all student scoring below proficiency by quarter. As students met goals for the quarter, we moved them out and moved in others. We had a targeted school wide writing assignments which required students to breakdown what they were reading and write use the RACE strategy, and all students received feedback from their teachers in August and December. We also offered morning tutoring and grade recovery. Finally, we had 2 incentive-based programs. The first was a partnership with Zaxby’s for a 5 Finger Meal if students improved their RI score 100 points or more. The second was a partnership with radio station V103 and DJ Greg Street as part of their WENEED2READ for $100 to 6 students (one girl & boy per grade level) who had the most RI growth. |

| Previous Year’s Goal #2 | Decrease the percentage of students scoring below proficiency by 10% on the Math Inventory for grades 6-8. |
| --- | --- |
| Was the goal met? ☒ YES ☐ NO |  |
| What data supports the outcome of the goal? | In August of 2021 we had 689 students scoring below proficiency on the Math Inventory for grade 6-8. In April of 2022 we had 323 students scoring below proficiency on the Math Inventory for grade 6-8. That is a 53.12% decrease! |
| Reflecting on Outcomes |  |
| If the goal was not met, what actionable strategies could be implemented to address the area of need? |  |
| If the goal was met or exceeded, what processes, action steps, or interventions contributed to the success of the goal and continue to be implemented to sustain progress? | We had targeted math support classes for all student scoring below proficiency by quarter. As students met goals for the quarter, we moved them out and moved in others. We had a targeted school wide math word problem strategy which required students to breakdown what they were reading and write the evidence using the CUBES strategy. We also had 360o math boards allowing for formative feedback by math teachers. We also offered morning tutoring and grade recovery. Finally, we had a tiered incentive program. The first was a partnership with Zaxby’s for a 5 Finger Meal if students improved their MI score 100 points or more. In addition, students could win ice cream, a slushie, chips etc. depending on where they fell in improving their score 75, 50 or 25 points. |

| Previous Year’s Goal #3 | Decrease the percentage of students receiving an office referral by 10% for grades 6-8. |
| --- | --- |
| Was the goal met? ☒ YES ☐ NO |  |
| What data supports the outcome of the goal? | We had to start a baseline from 2019-2020, which was the last year we were fully operational (i.e., 2020-2021 we were less than half meeting in-person due to COVID). Per the Cobb County Student Information System (CSIS) we had a 25.5% decrease in the number of students receiving 1 or more discipline referrals. However, it should be noted that we also had 400 students less due to a new middle school AND we did not have an entire 4th quarter (9 weeks) in Spring 2020 due to COVID. |
| Reflecting on Outcomes |  |
| If the goal was not met, what actionable strategies could be implemented to address the area of need? |  |
| If the goal was met or exceeded, what processes, action steps, or interventions contributed to the success of the goal and continue to be implemented to sustain progress? | While the goal was exceeded, we feel the data is not comparable due to COVID and the opening of a new middle school. We will keep the same goal for next year as the population size will stay the same, along with the additional 9 weeks being present 2 years in a row. In terms of success, we did a lot of student incentives through PBIS, Fresh Air Fridays, and PTSA Celebrations where students had to earn their way into the events by not receiving discipline. We will continue to provide students with training on being respectful, responsible, and safe, and embodying the 10 IB character traits. We will also continue with interventions such as counselor led groups and restorative practices (circles and conferences). |

Comprehensive Needs Assessment – Summary of Findings (Schoolwide)

| Data | Identified Strengths | Identified Challenges | Multiple Data Sources |
| --- | --- | --- | --- |
| ELA | 94% of students pass ELA on their report card. - Understanding literary texts - Speaking on topic Moby Max, Flocabulary and IXL are used in and out of the classroom thanks to the laptops. | For the 6% not passing, few attended grade repair - Informational text vocab - Ability to draw inferences We still have about 15% of students that did not opt in for a laptop. | Synergy Report Card Common Formatives Reading Inventory Grade Recovery Data Software Data |
| Math | 88% of students pass Math on their report card. - Solving simple operations - Solving single-step problems Moby Max and IXL are used in and out of the classroom thanks to the laptops. | Not enough students attend grade recovery. - Fluency of basic math facts - Drawing inferences from word problems We still have about 15% of students that did not opt in for a laptop. | Synergy Report Card Common Formatives Math Inventory Grade Recovery Data Software Data |
| Science |  |  |  |
| Social Studies |  |  |  |
| Discipline / School Climate Data | Skipping is no longer in the top 10 for discipline. They are coming to class. Discipline incentives for the spring kept a lot of students out of trouble in 8th grade. | Our top discipline continues to be insubordination, class disruption and inappropriate horseplay. Inconsistent use of PBIS points, inconsistent use of the infraction steps prior to being a referral. | CSIS Discipline Data PBIS Rewards App |
| Professional Learning What’s been provided? What is the impact? | We provided training to teachers, students and parents on the new grading rubric which assisted in the passing of classes for mastery of standard vs. behavior such as late work or missing work. | We need a complete retraining on the PBIS Rewards APP for teachers, students, and parents. | IB Training Quarterly Grade Reports Late Work Policy Missing Work Policy |
| Other |  |  |  |

9

9

Comprehensive Needs Assessment – Summary of Findings (Student Groups)

| Data | Student Groups | Identified Strengths | Identified Challenges | Multiple Data Sources |
| --- | --- | --- | --- | --- |
| ELA | ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | GAPS are being closed via Reading Support classes. SWD students grew from below basic to basic. Increased participation by Black students in Advanced Content ELA EL students grew in language acquisition. | Not enough economically disadvantaged students attend morning grade recovery due to transportation issues and not enough opted-in for a laptop (although hotspots were offered). | Synergy Student Rosters Reading Inventory ACCESS Testing Grade Recovery Data Software Data |
| Math | ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | GAPS are being closed via Math Support classes. SWD students grew from below basic to basic. Increased participation by Black students in Advanced Content Math. EL students grew their math vocabulary knowledge. | Not enough economically disadvantaged students attend morning grade recovery due to transportation issues and not enough opted-in for a laptop (although hotspots were offered). | Synergy Student Rosters Math Inventory ACCESS Testing Grade Recovery Data Software Data |
| Science | ☐ Econ. Disadvantaged ☐ English Learners ☐ Special Ed. ☐ Foster/Homeless ☐ Race / Ethnicity ☐ Migrant |  |  |  |
| Social Studies | ☐ Econ. Disadvantaged ☐ English Learners ☐ Special Ed. ☐ Foster/Homeless ☐ Race / Ethnicity ☐ Migrant |  |  |  |
| Discipline / School Climate Data | ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | 75% decrease in skipping 60% decrease in insubordination 60% decrease in class disruption | Horseplay continues to be an issue, even with 400 less students, it just barely met the goal at a 15% decrease. Tik Tok Challenges did not help! | CSIS Discipline Data PBIS Infractions |
| Professional Learning | ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | More teachers became certified in ESOL, SPED, Gifted, and technology. Software training on IXL, Dreambox, Flocabulary, Moby Max. | PBIS is not utilized with fidelity Software needs | End of year certifications list End of year degrees list Software Usage Reports |
| Other | ☐ Econ. Disadvantaged ☐ English Learners ☐ Special Ed. ☐ Foster/Homeless ☐ Race / Ethnicity ☐ Migrant |  |  |  |

| Overarching Challenge #1 | All students need to be able to read and write on grade level. |
| --- | --- |
| Root Cause #1 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need exposure to teaching different types of students to better understand the collaboration needed to reach all students. |
| Root Cause #2 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to implement strategies to help students learn how to use context clues and prior knowledge to define unknown words. |
| Root Cause #3 - (Within control) Impacts which system(s): ☐ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☐ Supportive Learning Environment ☐ Family Engagement | Teachers need professional learning in differentiated strategies for teaching students how to write. |
| Contributing Factors (Outside of control) | Parents not understanding the reading inventory scores of their students and how they can help increase the scores. |
| Goal Specific, Measurable, Achievable, Relevant, Timebound | Decrease the percentage of students scoring below proficiency by 10% on the Reading Inventory grades 6-8. |

| Overarching Challenge #2 | All students need to be able to perform on grade level in math. |
| --- | --- |
| Root Cause #1 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to provide more support in helping students understand mathematical vocabulary. |
| Root Cause #2 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to implement strategies to help students apply number sense without a calculator. |
| Root Cause #3 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to model problem-solving skills for real world math problems and provide background knowledge. |
| Contributing Factors (Outside of control) | Parents that do not understand the math inventory scores of students and how to help their students at home. |
| Goal Specific, Measurable, Achievable, Relevant, Timebound | Decrease the percentage of students scoring below proficiency by 10% on the Math Inventory for grades 6-8. |

| Overarching Challenge #3 | All students need to demonstrate social emotional awareness and self-control. |
| --- | --- |
| Root Cause #1 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☐ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to provide lessons regarding CMS behavior expectations of being respectful, responsible, and safe. They need specific examples of what it looks like and what they achieve when exhibiting these qualities. |
| Root Cause #2 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☐ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to utilize the PBIS Awards App and infraction system more effectively. |
| Root Cause #3 - (Within control) Impacts which system(s): ☒ Coherent Instruction ☒ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | Teachers need to provide International Baccalaureate lessons that promote MYIB global mindedness and the IB traits. Teachers need to provide lessons on being responsible, respectful, and safe. Teachers need additional training in restorative practices (circles and conferences). |
| Contributing Factors (Outside of control) | Social media and peers. |
| Goal Specific, Measurable, Achievable, Relevant, Timebound | Decrease the percentage of students with an office referral for grades 6-8. |

| School Improvement Goals Include goals on the parent compacts and policy |  |
| --- | --- |
| Goal #1 | Decrease the percentage of students scoring below proficiency by 5% for grades 6-8 as measured by the August 2002 to May 2023 Reading Inventory. |
| Goal #2 | Decrease the percentage of students scoring below proficiency by 5% for grades 6-8 as measured by the August 2002 to May 2023 Math Inventory. |
| Goal #3 | Decrease the percentage of students receiving discipline consequences by 5% for grades 6-8 as measured by the 2022-2023 discipline data. |
| Goal #4 |  |

| Title I Personnel/Positions Hired to Support the School Improvement Goals SWP Checklist 2.c(iv) |  |  |  |
| --- | --- | --- | --- |
| Position | Supports Goal(s) | System | What activities is the position responsible for and how will that impact the Schoolwide Plan? |
| ELA Academic Coach Math Academic Coach | ☐ All ☒ Goal 1 ☒ Goal 2 ☐ Goal 3 ☐ Goal 4 | ☒ Coherent Instruction ☒ Professional Capacity ☒ Effective Leadership ☐ Supportive Learning Environment ☐ Family Engagement | Coaches will support teachers with implementing reading and writing strategies across all content areas & connections including Think Aloud, Quick Write Prompts, List-Group-Label, & R.A.C.E strategy. Lesson/unit plans will be monitored to ensure the strategies are being implemented. These practices will improve test scores (formative and summative), increased content comprehension, and help close achievement gaps. Coaches will support math teachers with implementing and using annotation skills (CUBES strategy) when solving real-world mathematical problems. They will also continue to support teachers with implementation of the 360o math classroom (white boards) for quick formative assessments and student collaboration. These practices will improve test scores (formative and summative), increased content comprehension, and help close achievement gaps. Coaches will monitor software usage reports and collect data monthly. All reports will be shared with teachers during weekly CCCs and with the building leadership team during monthly meetings, and faculty during monthly meetings. |
| Parent Facilitator | ☒ All ☐ Goal 1 ☐ Goal 2 ☐ Goal 3 ☐ Goal 4 | ☐ Coherent Instruction ☐ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☒ Family Engagement | Communicate and share the Parent Compact with all stakeholders, communicating the school wide reading, writing, and math strategies, Open House, academic night, and meetings with parent engagement committee. |
| Math Support Teacher | ☐ All ☐ Goal 1 ☒ Goal 2 ☐ Goal 3 ☐ Goal 4 | ☒ Coherent Instruction ☐ Professional Capacity ☐ Effective Leadership ☒ Supportive Learning Environment ☐ Family Engagement | The teacher will support an identified group of below proficiency students by providing foundational math skills to meet the standards for the grade level. This teacher will work with students daily to get them to a basic understanding of the grade level math content to successfully function in the regular classroom. The teacher will use the appropriate software to individualize student content to improve comprehension and help close learning gaps. |

| GOAL #1 | Decrease the percentage of students scoring below proficiency by 10% on the Reading Inventory for grades 6-8 between August 2022 and May 2023. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Step(s) SWP Checklist 2.a, 2.b, 2.c(i), 2.c(ii), 2.c(iv),2.c(v) | Resources | Funding Source(s) SWP Checklist 5.e | Start Date | How will the action step be implemented? What artifacts will be used to show implementation? SWP Checklist 3.a | What is the desired outcome of the action step? What evidence will be used to evaluate the outcome? SWP Checklist 3.a | Person Responsible |
| Schoolwide implementation of reading and writing strategies: - Think Aloud - Quick Write Prompts - List-Group-Label - R.A.C.E Provide professional learning on the strategies, along with classroom support and modeling for all teachers needing additional training via walk thru data and lesson plan checks. Additional professional learning will include ELA targeted conferences, as well as IB workshops aligned to reading/writing. | Subs for collaboration Classroom materials: writing prompts, classroom libraries Professional learning books regarding writing strategies District ELA Trainings IB Reading & ELA Workshop & Conferences GA Council of ELA Teachers Conference | Title I Funds District Funds Local School Funds District Funds Title 1 Funds Title 1 Funds | August 22 | Implementation: Coaches and department lead will check weekly lesson plans outlined in the IB unit plans to ensure strategies are used. Coaches will observe strategies in action and identify professional learning needs. Leadership team will discuss the implementation of these strategies to determine where support and the expectations for implementation should be provided. Artifacts: lesson plans, walk through data, CCC agendas | Desired Outcome: Grade levels will discuss impact of strategies during CCCs as seen on Common Formative / Summative Assessments. Meeting minutes will specifically indicate which strategy was used and the potential impact on student achievement. Evidence: CTLS Score Reports, student writing samples, summarized formative assessment data | ELA Teachers ELA Coach ELA Admin |
| English Language Arts teachers will preview vocabulary prior to reading and conference with students monthly to discuss independent reading. Flocabulary will be implemented in all ELA classrooms to support vocabulary instruction. | Flocabulary | District Funds | August 22 | Implementation: Lesson plan and student portfolios will be reviewed by Title I coaches every two weeks to ensure vocabulary is being taught consistently. Artifacts: Lesson plans, student portfolios | Desired Outcome: Student vocabulary scores will increase as evidenced by RI scores, Flocabulary usage reports and common formative vocabulary tests. Teachers will discuss vocabulary improvement at CCCs monthly. Evidence: Flocabulary usage report, summarized vocabulary assessment data, CCC minutes | ELA Teachers Title 1 Coach ELA Admin |
| Differentiate ELA instruction for remedial, on level and enrichment students. Software programs IXL ELA and Moby Max will be implemented with fidelity as a supplemental resource to meet the various needs of all learners. | IXL ELA Moby Max | Title 1 Funds Title 1 Funds | August 2022 | Implementation: Academic coach will monitor the usage reports for all software programs to ensure implementation with fidelity. Usage reports will be reviewed monthly during admin team meetings and teacher recognitions for program usage will be highlighted monthly. Artifacts: Usage reports to be reviewed to ensure implementation with fidelity | Desired Outcome: Growth reports for all software programs will be monitored monthly and discussed by teachers in CCCs. Academic coaches and content leads will continue to provide professional learning for best strategies as needed. Evidence: RI and software growth reports reviewed to ensure positive impact of software, CCC minutes | ELA Teachers Title 1 Coach ELA Admin |
| Identify students using RI reports to provide intentional and targeted support through multiple interventions: Reading Support Class – Students with an RI score in the lowest 25 percentile will be scheduled into Read 180 Morning tutoring - Students with an RI score below proficiency will be invited to tutoring. Quarterly grade recovery - Students with a grade of 65% to 69% will be offered the opportunity to make up work to improve the final grade. | Reading Support Teacher Morning Tutors Read 180 Materials Grade Recovery Teacher | District Funds Cares Act Title I District Funds 20 Day Funds | August 2022 | Implementation: Academic coach will work with the school scheduler to ensure the right students are offered Read 180 services. Coaches will monitor Tutoring and Grade Recovery Sign in sheets to determine if the intervention is being utilized by students. Coaches will create an incentive program for student growth after each administration of the assessment. Artifacts/Evidence: Read 180, tutoring and Grade Recovery rosters. | Desired Outcome: Read 180 and RI scores will be reviewed with teacher and admin every two weeks and instruction will be revised accordingly. Classroom assessments will be monitored for students participating in tutoring to determine impact of tutoring and if revisions are needed. Additionally, the percentage of students attending grade recovery who earned a higher grade will be reviewed. Evidence: RI scores, classroom assessments, and Read 180 Growth Reports. | Reading Support Teachers Title 1 Coach ELA Admin |

| GOAL #2 | Decrease the percentage of students scoring below proficiency by 10% on the Math Inventory for grades 6-8 between the August 2022 and May 2023 assessments. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Step(s) SWP Checklist 2.a, 2.b, 2.c(i), 2.c(ii), 2.c(iv),2.c(v) | Resources | Funding Source(s) SWP Checklist 5.e | Start Date | How will the action step be implemented? What artifacts will be used to show implementation? SWP Checklist 3.a | What is the desired outcome of the action step? What evidence will be used to evaluate the outcome? SWP Checklist 3.a | Person Responsible |
| Implement student collaboration to improve understanding of math concepts and the communication of mathematical reasoning. Use the 360-math model to create collaborative space for students and provide teachers a way to monitor student understanding through brief, immediate formative assessments. Provide professional learning on the strategies, along with classroom support and modeling for all teachers needing additional training via walk thru data and lesson plan checks. Additional professional learning will include Math targeted conferences, as well as IB workshops aligned to math. | 360 White Boards Math Manipulatives Professional learning books regarding math strategies District Math Trainings IB Math Workshops & Conferences GA Council of Math Teachers Conference | Title 1 Funds District Funds Local School Funds District Funds Title 1 Funds Title 1 Funds | August 2022 | Implementation: Coaches and department lead will check weekly lesson plans for differentiated strategies implementation. Artifacts/Evidence: Lesson plans, walk through data | Desired Outcome: Grade levels will discuss impact of strategies during CCCs as seen on Common Formative / Summative Assessments. Meeting minutes will indicate strategy used and impact on student growth. Evidence: CTLS Score Reports, common formative assessments, CCC meeting minutes and summary data | Math Teachers Title 1 Coach Math Admin |
| Improve problem solving skills using the CUBES (Circle, Underline, Box, Eliminate, Solve) Strategy. All students will use this process when solving word problems. Plus, teachers will train students to effectively use the calculator and other manipulatives for more complex problems (including fractions / square roots / etc.). Teachers will integrate unit vocabulary into weekly assessments. | CUBES Templates Calculators | Title 1 Funds District | August 2022 | Implementation: Coaches check weekly lesson plans outlined in the unit plan to ensure strategies are used. Coaches observe strategies in action and identify professional learning needs. Admin will discuss the implementation of strategies to determine additional support needs. Artifacts: Lesson plans, walk through data | Desired Outcome: Grade levels will discuss impact of strategies during CCCs as seen on Common Formative / Summative Assessments. Meeting minutes will indicate which strategy was used and impact on student achievement. Evidence: CTLS Score Reports, CCC meeting minutes summarizing data | Math Teachers Title 1 Coach Math Admin |
| Utilize software packages – IXL and Moby Max to support math literacy in 21st century classrooms. These programs provide differentiation for remedial, on-level, and enrichment purposes for Math teachers. These are additional resources for teachers to use to ensure student success. These programs are aligned with GA standards and content specific math literacy skills. Students can use the programs to help them acquire test taking skills. | IXL Math Moby Max | Title 1 Funds Title 1 Funds | August 2022 | Implementation: Academic coach will monitor the usage reports for all software programs to ensure implementation with fidelity. Usage reports will be reviewed monthly during admin team meetings and teacher recognitions for program usage will be highlighted monthly. Artifacts: Usage reports | Desired Outcome: Growth reports for all software programs will be monitored monthly and discussed by teachers in CCCs. Academic coaches and content leads will continue to provide professional learning for best strategies as needed. Evidence: growth reports, Reading Inventory | Math Teachers Title 1 Coach Math Admin |
| Identify students using MI reports to provide intentional and targeted support through multiple interventions: Math Support class – Students with an MI score in the lowest 25 percentile will be scheduled into Math Support Intensive Math Support Class for Els and SWD Students with an MI score in the lowest 25 percentile and meeting the criteria will be schedules into this class. Morning tutoring - Students with an MI score below proficiency will be invited to tutoring. Quarterly grade recovery - Students with a grade of 65% to 69% will be offered the opportunity to make up work to improve the final grade. | Math Support Teacher #1 Math Teacher Teacher #2 Morning Tutors Dream Box Materials Grade Recovery Teacher | Title 1 District Funds (Cares Act) Title I District Funds 20 Day Funds | August 2022 | Implementation: Academic coach will work with the school scheduler to ensure the right students are offered math support services. Coaches will monitor Tutoring and Grade Recovery Sign in sheets to determine if the intervention is being utilized by students. Coaches will create an incentive program for student growth after each administration of the assessment. Artifacts/Evidence: Dream Box, tutoring and Grade Recovery rosters. | Desired Outcome: Dream Box and MI scores will be reviewed with teacher and admin every two weeks and instruction will be revised accordingly. Classroom assessments will be monitored for students participating in tutoring to determine impact of tutoring and if revisions are needed. Additionally, the percentage of students attending grade recovery who earned a higher grade will be reviewed. Artifacts/Evidence: MI scores, classroom assessments, and Math Support Growth Reports. | Math Support Teachers Title 1 Coach Math Admin |

| GOAL #3 | Decrease the percentage of students with an office referral by 10% for grades 6-8 in 2023 when compared to data from 2022. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Step(s) SWP Checklist 2.a, 2.b, 2.c(i), 2.c(ii), 2.c(iv),2.c(v) | Resources | Funding Source(s) SWP Checklist 5.e | Start Date | How will the action step be implemented? What artifacts will be used to show implementation? SWP Checklist 3.a | What is the desired outcome of the action step? What evidence will be used to evaluate the outcome? SWP Checklist 3.a | Person Responsible |
| Delivering explicit lessons and examples of being safe, responsible, and respectful as part of PBIS to improve school safety and promote positive behavior. This is done weekly during homeroom advisement. Structured Morning Advisement SEL Mondays (Counselors) 2nd STEP Tuesdays PBIS Wednesday IB Thursday Student Support Fridays | PBIS APP PBIS Trainings & Workshops PBIS Conferences PBIS Lessons Restorative Circles Training & Conferences | Title 1 Local Funds Title 1 Local School District Funds & Title 1 | August 2022 | Implementation: PBIS Committee will plan weekly school-wide lessons to engage students during homeroom advisement period. Homeroom teachers will train students how to access the PBIS reward system for independent monitoring, goal setting, and self-regulation. Artifacts: PBIS Lesson Plans | Desired Outcome: Administrators will review CSIS Discipline System weekly with PBIS Committee to implement positive behavioral strategies. Strategies used will be discussed as a school community and/or grade level for overall effectiveness. Evidence: PBIS Infractions CSIS Discipline System | Counselors PBIS Committee APs |
| Students are explicitly taught the ten IB Traits for global mindedness to promote personal intellectual, emotional, and social growth. | IB Framework | Local School | August 2022 | Implementation Committee will plan weekly school-wide lessons to engage students during homeroom advisement period. Artifacts: Lesson plan samples | Desired Outcome: Administrators will review CSIS Discipline System and PBIS Database weekly to implement positive behavioral strategies. Each month a student will be identified for exhibiting the IB trait. Strategies used will be discussed as a school community and/or grade level for overall effectiveness. Evidence: CSIS Discipline System/PBIS Database Infractions | MYP IB Coordinator MYP IB Committee APs |
| Provide students approaches to learning skills and the attributes of the IB learner profiles by implementing the International Baccalaureate Program frameworks. | IB Framework | Local School | Ongoing | Implementation: Academic coaches will work with teachers to create interdisciplinary unit plans that include the ATL skills and Learner Profiles. Coaches will create weekly lessons for teachers to explicitly teach IB traits and ATL skills. Artifacts/Evidence: Lesson plan, student reflection journal. | Desired Outcome: Grade level will discuss the implementation and impact of ATL skills and IB traits. Meeting minutes will specifically indicate which skill/trait was used and the potential impact on student success. Evidence: CCC minutes | ELA Teachers Title 1 Coach ELA Admin |
| Students are explicitly taught 2nd STEP and the process of restorative circles to promote social-emotional development, safety, and the well-being of middle school child. | 2nd Step Program | District Funds | August 2022 | Implementation Academic coach will plan weekly school-wide lessons to engage students during homeroom advisement period. Artifacts: Lesson Plan Samples | Desired Outcome: Administrators will review CSIS Discipline System and PBIS Database weekly to implement positive behavioral strategies. Evidence: CSIS Discipline System/PBIS Database Infractions | Coaches District 2nd Step Team APs |

| Actions to Assist Student Groups in Meeting School Improvement Goals |  |  |  |
| --- | --- | --- | --- |
| Student Group(s) SWP Checklist 2.a, 2.b, 2.c(i), 2.c(ii) | Action steps to improve/support achievement of student groups | Resources | Funding Source |
| ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | Check & Connect is an intervention used with students who show warning signs of disengagement with school, such as poor attendance, behavioral issues, and/or low grades. The "Check" component refers to the process where mentors systematically monitor student absences, tardies, behavioral referrals, and grades. The "Connect" component refers to mentors providing personalized, timely interventions to help students solve problems, build skills, and enhance competence | Check and Connect | Title I and District Funds |
| ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | Sources of Strength is a suicide prevention project designed to harness the power of peer social networks to change unhealthy norms and culture, ultimately preventing suicide, bullying, and substance abuse. This model strengthens multiple sources of support (protective factors) around young individuals so that when times get hard, they have strengths and peers to rely on. | Sources of Strength | District Funds |
| ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | Restorative Practices is a social science that studies how to strengthen relationships between individuals as well as social connections within the school. Circles proactively builds the skills individuals need when conflicts arise because they give every individual the opportunity to speak and be heard. Conferences are mediated dialogue between individuals and those responsible for causing the issue. | Restorative Practices | Title I |
| ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | PBIS Rewards is a system that assists schools in their Positive Behavioral Interventions and Support program. The multi-device platform makes it easy to continuously recognize students for meeting behavior expectations from anywhere in the school, not just the classroom. | PBIS Application | Title I |
| ☒ Econ. Disadvantaged ☒ English Learners ☒ Special Ed. ☐ Foster/Homeless ☒ Race / Ethnicity ☐ Migrant | Teacher Mentors are committed to their students and teaching. Members interact regularly while reflecting and refining, sharing stories, and problem-solving together. Mentorship has the power to impact the course of students’ academic and personal life trajectories. | Teacher Mentors | Title I |

| Family Engagement Plan to Support School Improvement (Required Components) |  |  |  |
| --- | --- | --- | --- |
| Family Engagement Activities (Must be listed in the school policy) | Date(s) Scheduled | Date Completed | “Shall” Standard(s) Addressed |
| 1. Required State of the School Meeting – Deadline September 30, 2022 Parents will learn about Title I, how our school spends Title funds (budget snapshot), highlights of the schoolwide plan, description of curriculum and assessments used, our school compacts and policies, professional qualifications of our teachers, and opportunities for family engagement including use of the family resource center. | 9/22/2022 |  | ☒ 1 ☐ 4 ☐ 2 ☐ 5 ☐ 3 ☐ 6 |
| 2. Required Fall Input Survey/ Evaluation (secondary method) – Deadline October 30, 2022 Parents will have the opportunity to assist in planning future family engagement activities, revising our school policy and compact, and considering how to spend our family engagement funds. | 10/17/2022 |  | ☐ 1 ☐ 4 ☐ 2 ☐ 5 ☐ 3 ☒ 6 |
| 3. Required Spring Input Meeting and Survey (primary method) – Deadline April 28, 2023 Parents will have the opportunity to assist in planning future family engagement activities, revising our school policy and compact, and considering how to spend our family engagement funds. | 3/28/2023 |  | ☐ 1 ☐ 4 ☐ 2 ☐ 5 ☐ 3 ☒ 6 |
| 4. Required FOUR Building Staff Capacity Opportunities (Do not need to be listed in the Policy) Teacher will continue to learn about the value and utility of contributions of parents including how to reach, communicate with, and work with parents to implement parent programs and build ties between the parents and school Deadlines: PL#1 9/23/22 ¦ PL#2 12/9/22 ¦ PL#3 2/17/23 ¦ PL#4 4/28/23 | 9/13/2022 |  | ☐ 1 ☐ 4 ☐ 2 ☐ 5 ☒ 3 ☐ 6 |
|  | 11/15/2022 |  |  |
|  | 1/31/2023 |  |  |
|  | 4/20/2023 |  |  |
| 5. Required Transition Activities for students entering or exiting our school (Multiple options, not just visit the school) Parents will have an opportunity to learn about the next grade level in their child’s education. Briefly describe the transition activities here: Open House 8th Grade Parent Night Rising 6th Grade Parent Night | 8/22/2022 9/22/2022 2/28/2023 |  | ☐ 1 ☒ 4 ☐ 2 ☐ 5 ☐ 3 ☐ 6 |
| 6. Required: Provide information related to school and parent/programs meetings in a format and language parents can understand. SWP Checklist 5.d | List documents translated for parents: Parent Compact Weekly Newsletter Conference Week Emails |  | ☐ 1 ☐ 4 ☐ 2 ☒ 5 ☐ 3 ☐ 6 |

| School Developed Family Engagement Activities (Required for “Shall’s” 2 and 6) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Developed Family Engagement Activities (Must be listed in the school policy) | “Shall” Addressed | Goal(s) Addressed | Resources | Funding Source(s) SWP Checklist 5.e | Date | How is the activity monitored, and evaluated? Include data/artifacts to be collected as evidence. | Team Lead |
| - Open House - Title I Nights | ☐ 1 ☒ 2 ☐ 3 ☐ 4 ☐ 5 ☒ 6 | ☒ Goal 1 ☒ Goal 2 ☐ Goal 3 ☐ Goal 4 | Handouts Brochures | CCSD CCSD | August 2022 September 2022 March 2023 | Sign-in Sheet Ticket Out the Door | APs Coaches Grade Level Lead |
| - Family-Teacher Conferences - Family Curriculum Nights | ☐ 1 ☒ 2 ☐ 3 ☐ 4 ☐ 5 ☒ 6 | ☒ Goal 1 ☒ Goal 2 ☐ Goal 3 ☐ Goal 4 | RI/MI Scores RACE Strategy CUBES Strategy Lite Snacks | CCSD CCSD CCSD Title 1 | October 2022 February 2023 | Sign-in Sheet Ticket Out the Door | APs Coaches CCC Subject Lead |
| - School-Community Projects - Volunteering within the School | ☐ 1 ☒ 2 ☐ 3 ☐ 4 ☐ 5 ☐ 6 | ☐ Goal 1 ☐ Goal 2 ☒ Goal 3 ☐ Goal 4 | Campus Clean Up WENEED2 READ IB 8th Grade Project | Local Local Local | October 2022 February 2023 March 2023 | Sign-in Sheet for 8th grade project / community service hours. WENEED2READ Signed logs and RI Scores | Media Center Specialist APs Coaches |

GaDOE required six “Shall’s”.  Each shall must be addressed at least once during the school year:

- Assist parents in understanding state academic standards, state and local assessments, and how to monitor their child’s academic progress.

- Provide materials and training to help parents work with their child to improve academic achievement. (Ex. Literacy training, technology training)

- Educate school staff in the value and utility of the contributions of parents, and how to reach, communicate with, and partner with parents to implement parent programs to build ties between parents and the school.

- Coordinate and integrate parent programs and activities with other Federal, State, and local programs (Preschool to Kindergarten, transitions, parent resource centers, etc.) to support parents in more fully participating in their child’s education.

- Ensure information related to school and parent programs/meetings are sent in a format and language parents can understand.

- Provide other reasonable support for parental involvement activities as parents may request.  These are school developed activities based upon parent input.

(#14 in list of “shalls” and “mays”)

School Improvement Plan Required Questions

Schoolwide Plan Development – Section 1114(2)(B) (i-iv)

1. Cobb County’s schoolwide plans are developed during a 1-year period; unless – the school is operating a schoolwide program on the day before the date of the enactment of Every Student Succeeds Act, in which case such school may continue to operate such program but shall develop amendments to its existing plan during the first year of assistance after that date to reflect the provisions of the section. Evidence to support this statement includes: The dated schoolwide plans, dated budget meeting agendas and signature pages, and dated committee and input meeting signature pages. SWP Checklist 5(a)

2. Cobb County’s schoolwide plans are developed with the involvement of parents and other members of the community to be served and individuals who will carry out such plan, including teachers, principals, other school leaders, paraprofessionals present in the school, administrators (including administrators of programs described in other parts of this title), the local educational agency, to the extent feasible, tribes and tribal organizations present in the community, and , if appropriate specialized instructional support personnel, technical assistance providers, school staff, if the plan relates to a secondary school, students, and other individuals determined by the school. Evidence to support this statement includes: The schoolwide plan committee signature page and the Family Engagement fall and spring input meetings. Schoolwide Checklist 5(b)

3. Cobb County’s schoolwide plans remains in effect for the duration of the school’s participation under Sec. 114(b)(1-5) of ESSA, except that the plan and its implementation shall be regularly monitored and revised as necessary based on student needs to ensure that all students are provided opportunities to meet the challenging State academic standards. Evidence to support this statement includes: The Title I midyear and end of year monitoring of SWP goals, monitoring and approving all Title I expenditures, and revision dates listed on the SWP cover page. SWP Checklist 5(c)

4. Cobb County’s schoolwide plans are available to the local education agency, parents, and the public, and the information contained in such plan shall be in an understandable and uniform format and, to the extent practicable, provided in a language that the parents can understand. Evidence to support this statement includes: Every Title I school post the Title I plan, Title I budget, and Family Engagement Components on the school’s website and in multiple languages. SWP Checklist 5(d)

5. Describe how the schoolwide plan has been developed in coordination and integration with other Federal, State and local services, resources, and programs, such as programs supported under this Act, violence prevention programs, nutrition programs, housing programs, Head Start programs, adult education programs, career and technical education programs, and schools implementing comprehensive support and improvement activities or targeted support and improvement activities under section 1111 (d), if appropriate and applicable. SWP Checklist 5(e) Include district initiatives that are supported with Title I Funds (For example: Early Literacy Framework (ELF), Math Fluency Initiative (MFI), LETRS, Read 180, etc.)

SCHOOL RESPONSE: READ 180 is a district initiative, as well as the math and reading support classes have provided for additional teaching positions. Title 1 positions have specific training for teachers and academic coaches.

ESSA Requirements to Include in the Schoolwide Plan – Section 1116(B)(1)

6. Jointly develop with, and distribute to, parents and family members of participating children a written parental and family engagement involvement policy, agreed on by such parents, that shall describe the means for carrying out the requirements of Subsections (c) through (f). Parents shall be notified of the policy in an understandable and uniform format and, to the extent practicable, provided in a language the parents can understand. Such policy shall be made available to the local community and updated periodically to meet the changing needs of parents and the school. Evidence to support this statement includes Posting every Title I school’s parent policy on the school’s website in multiple languages where practicable, Fall and Spring input meeting agendas and sign in sheets providing parents the opportunity to assist in the development of the school’s parent policy, compact and parent engagement budget. SWP Checklist 4

Evaluation of the Schoolwide Plan - 34 CFR § 200.26

7. Describe how the school regularly monitors and the implementation of, and results achieved by, the schoolwide program, using data from the State’s annual assessments and other indicators of academic achievement. SWP Checklist 3(a)

SCHOOL RESPONSE: The reading and math inventory are reviewed quarterly and reflected upon by subject area professional learning communities and administration to determine progress toward school goals in ELA and Math. In addition, course data (summative assessments and grades) are used in conjunction to ensure alignment.

8. Describe how the school determines whether the schoolwide program has been effective in increasing the achievement of students in meeting the challenging State academic standards, particularly for those students who had been farther from achieving the standards. SWP Checklist 3(b)

SCHOOL RESPONSE: The periodic review of data is compared to the end of year data goal and determined whether to be on target with the desired growth for the remaining time of the year.

9. Describe how the schoolwide plan will be revised, as necessary, based on regular monitoring to ensure continuous improvement of students in the schoolwide program. SWP Checklist 3(c)

SCHOOL RESPONSE: We revise the goals for achievement if exceeding or the implementation of additional programs when not on track.

Schoolwide Plan Reform Strategies – Section 1114(b)(7)(A)(i-iii)(I-V)

10. Address the reform strategies the school will implement to meet the school needs, including a description of how such strategies will: Provide opportunities for all children, including all subgroups defined in section 1111 (c)(2), to meet the State’s challenging academic standards. Evidence to support this statement includes: Specific schoolwide plan action steps, the method for monitoring and evaluating those action steps and the schoolwide plan student groups page specifically identifying supports to assist various student groups in meeting the State’s challenging academic standards, where applicable. SWP Checklist 2(a)

11. Address the reform strategies the school will implement to meet the school needs, including a description of how such strategies will: use methods and instructional strategies that strengthen an academic program in the school, will increase the amount and quality of learning time, and help provide an enriched and accelerated curriculum, which may include programs, activities, and courses necessary to provide a well-rounded education. Evidence to support this statement includes: Specific schoolwide plan action steps, the method for monitoring and evaluating those action steps, where applicable. SWP Checklist 2(b)

12. Address the reform strategies the school will implement to meet the school needs, including a description of how such strategies will: address the needs of all children in the school, but particularly the needs of those at risk of not meeting the challenging State academic standards through activities which may include - counseling, school-based mental health programs, specialized instructional support services and other strategies to improve students’ skills outside the academic subject areas. Evidence to support this statement includes: Specific schoolwide plan action steps, the method for monitoring and evaluating those action steps, where applicable. SWP Checklist 2(c)(i)

13. Describe the implementation of your schoolwide tiered model to prevent and address problem behavior and early intervening services, coordinated with similar activities and services carried out under the Individuals with Disabilities Education Act (20 U.S.C. 1400 et seq.). SWP Checklist 2.c(iii)

SCHOOL RESPONSE: We have RTI training, and meetings, and counselor programs that address disciplinary needs based on PBIS.

14. Describe professional development and other activities for teachers, paraprofessionals, and other school personnel to improve instruction and use of data from academic assessments, and to recruit and retain effective teachers, particularly in high need subjects. SWP Checklist 2.c(iv)

SCHOOL RESPONSE: - Mentor support from veteran teachers to those teachers that are new to our building - Instructional Coaching for any other teacher in need of support - Weekly collaborative team meetings focused on instruction and common assessment data - Targeted professional learning - facilitated by the academic coach - Monthly school-wide research-based instructional strategies presented by teacher leaders - Monthly instructional technology trainings - District - ESOL instructional trainings - IB Professional Learning with the IB Coordinator

15. ONLY MIDDLE AND ELEMENTARY SCHOOL RESPONSE REQUIRED Describe the transition activities provided for preschool children to kindergarten, 5th grade students to 6th grade and 8th grade students to 9th grade. SWP Checklist 2.c(v)

SCHOOL RESPONSE: - 8th Grade Articulation and Vertical Alignment with 9th grade teachers - 8th Grade Magnet Presentation - 8th Grade CITA Presentation (Cobb Innovation and Technology Academy) - 8th Grade Career Cruising, Reality U and College Field Trips - 8th Grade High School Art is offered for H.S. credit - 8th Grade High School Algebra 1 is offered for H.S. credit - 8th Grade High School Physical Science is offered for H. S. Credit - 8th Grade High School Spanish is offered for H. S. Credit - 8th Grade High School French is offered for H.S. Credit - Rising 6th Grade School Visits in March - Rising 6th Grade Informational Night

16. ONLY HIGH SCHOOL RESPONSE REQUIRED Describe how the school prepares and makes aware of opportunities for postsecondary education and the workforce, which may include career and technical education programs and broadening secondary school students’ access to coursework to earn postsecondary credit while still in high school (such as Advanced Placement, International Baccalaureate, dual or concurrent enrollment, or early college high schools. SWP Checklist 2.c(ii)

SCHOOL RESPONSE: Not Applicable

Comprehensive Needs Assessment – Section 1114(b)(1)(A)

17. Cobb County’s schoolwide plans are based on a comprehensive needs assessment of the entire school, that considers information on the academic achievement of children in relation to the challenging State academic standards, particularly the needs of those children who are failing, or are at-risk of failing, to meet the State academic standards and any other factors as determined by the local educational agency. Evidence to support this statement includes: The comprehensive needs assessment section of the schoolwide plan. SWP Checklist 1